## Tests
section no | test no | Relates to Ticket. | Is automated | Could be automated | Brief description of task/issue/function | Brief description of test | Expected Outcome | Pass/Fail | Comments | tester | test notes
1 | 1 |  | Yes | Yes | The server starts in an appropriate way | start_ibex_server | no errors | Pass |  | Bishal
1 | 2 |  | Yes | Yes | The server starts in an appropriate way | ISISDAE_01 runs (open console and type ENTER, verify its log is updated.) | ISISDAE_01 runs with no obvious errors in log | pass | Logs are located in Instrument\var\logs\ioc, to open console after running ibex server use console -M localhost IOCNAME (eg. ISISDAE_01) | Adam | added more instruction
1 | 3 |  | No | Yes | The server starts in an appropriate way | Check DBSVR runs when IBEX server starts. | DBSVR runs when IBEX server starts. | pass | Check start/ stop ioc dialog is populated, check log file for errors (In Ibex GUI IOC->start/stop IOCs) | Adam | added more instruction
1 | 4 |  | Yes | Yes | The server starts in an appropriate way | BLOCKSVR runs (as above) | no errors | Pass |  | Bishal
1 | 5 |  | No | No | The server starts in an appropriate way | Check PSCTRL runs when IBEX server starts. | PSCTRL runs when IBEX server starts. | Pass | Check start/stop ioc functionality works | Bishal
1 | 6 |  | No | No | The server starts in an appropriate way | Check IOCLOG runs when IBEX server starts. | IOCLOG runs when IBEX server starts. | Pass | Check messages appear in GUI IOC log, check log file for errors | Bishal
1 | 7 |  | No | No | The server starts in an appropriate way | Check JMS runs when IBEX server starts. | JMS runs when IBEX server starts. | Pass |  | Bishal
1 | 8 |  | No | No | The server starts in an appropriate way | Check RUNCTRL_01 runs when IBEX server starts. | RUNCTRL_01 runs when IBEX server starts. | Pass |  | Adam
1 | 9 |  | No | No | The server starts in an appropriate way | Check if an IOC can be started from local console e.g. console -M localhost EUROTHRM_01 | Local console works | Pass |  | Adam
1 | 10 |  | No | No | The server starts in an appropriate way | Check if an IOC can be started from remote console e.g. console -M NDXDEMO -l spudulike EUROTHRM_01 | Remote console works | Pass | flag is a lower case L | Bishal
1 | 11 |  | No | No | The server starts in an appropriate way | All of the IOCs in the current configuration start with the server | The IOCs in the current configuration (and set to auto-start) start when the server starts | Pass |  | Adam
2 | 1 |  | No | No | GeniePython is working | Using a shortcut open GeniePython | GeniePython Opens | Pass | In theory C:\Instrument\Apps\Python\genie_python should have a shortcut pointing to it. If not, simply run that script directly | Adam
2 | 2 |  | No | No | GeniePython is working | Using a python command window, run config_env.bat, then open python. In python: from genie_python.genie_startup import * | GeniePython imports successfully | Pass | will get the error "ERROR: IPython does not exist, auto complete not installed" | Adam
2 | 3 |  | No | Perhaps | GeniePython Autocomplete | In both scripting window and genie_python console type 'load_script("' then press tab | Shows auto complete for files in c:\scripts | Pass |  | Bishal
3 | 1 |  | Yes | Yes | The GUI start in an appropriate way | Launch GUI | GUI launches | Pass |  | Adam
3 | 2 |  | No | No | The GUI start in an appropriate way | check help/about in GUI | pop-up has expected values |  | check with Jenkins build/commit numbers and java version
3 | 3 |  | Yes | Yes | Dashboard Perspective | Open Dashboard | Dashboard loads with appropriate data | Pass |  | Adam
3 | 4 |  | Yes | Yes | Blocks Perspective | Load Blocks | Blocks load according to the current config | Pass |  | Adam
3 | 5 |  | No | No | Blocks Perspective | Make sure there are no half visible blocks | no half visible blocks | Pass |  | Adam
3 | 6 |  | No |  | Buttons perspective is working | Check button behaviour on alarms button | flashing if there is an alarm, steady red if alarm has been viewed | Pass | Switched to POLREF and checked. | Bishal
3 | 7 |  | Yes | Yes | Buttons perspective is working | Can switch between perspectives | switch successfully | Pass |  | Bishal
4 | 1 |  | No | Yes | Alarms Perspective | Opens when the button is selected | The alarm perspective opens in the large central panel | Pass |  | Bishal
4 | 2 |  | No | Perhaps | Alarms Perspective | Open alarms tree | Displays an appropriate tree of alarms | Pass |  | Bishal
5 | 1 |  | Yes | Yes | Beam Status Perspective | Switch to beam status perspective | Opens when the button is selected | Pass |  | Bishal
5 | 2 |  | Yes | Yes | Beam Status Perspective | Check beam information panel | The beam status info is shown | Pass | No beam, as we are out of cycle | Bishal
5 | 3 |  | Yes | Yes | Beam Status Perspective | check MCR news panel | MCR news is shown | Pass |  | Bishal
5 | 4 |  | Yes | Yes | Beam Status Perspective | Check Beam current panel | the beam current is shown | Pass |  | Bishal
6 | 1 |  | Yes | Yes | DAE Perspective |  | Opens when the button is selected | Pass |  | Bishal
6 | 2 |  | Yes | Yes | DAE Perspective | Start a run | Run starts | Pass |  | Bishal
6 | 3 |  | Yes | Yes | DAE Perspective | End a run | Run ends | Pass |  | Bishal
6 | 4 |  | Yes | Yes | DAE Perspective | pause run (start first) | Run pauses | Pass |  | Bishal
6 | 5 |  | Yes | Yes | DAE Perspective | Resume run (pause first) | Run resumes | Pass |  | Bishal
6 | 6 |  | Yes | Yes | DAE Perspective | Abort run | Run aborts | Pass |  | Bishal
6 | 7 |  | Yes | Yes | DAE Perspective | Cancel the abort | Run abort cancels | Pass |  | Bishal
6 | 8 |  | Yes | Yes | DAE Perspective | Switch between tabs (and sub-tabs) when the instrument is running | Tabs switch | Pass |  | Bishal
6 | 9 |  | Yes | Yes | DAE Perspective | Can switch between tabs (and sub-tabs) when the instrument is not running | Tabs switch | Pass |  | Bishal
6 | 10 |  | Yes | Yes | DAE Perspective | Check Experiment Setup sub-tabs while instrument is running | Contents are disabled | Pass |  | Bishal
6 | 11 |  | Yes | Yes | DAE Perspective | Check Experiment Setup sub-tabs while instrument is NOT running | Contents are enabled | Pass |  | Bishal
6 | 12 |  | No | YES | DAE Perspective | Run Summary Tab: specify a filter value in the drop-down menu | Log message table only shows messages with a severity equal or higher than the filter value | Pass |  | Bishal
6 | 13 |  | Yes | Yes | DAE Perspective | Experiment Setup, Time Channels: select a new time channel file without clicking 'Apply changes' | Does not update the current file | Pass |  | Bishal
6 | 14 |  | Yes | Yes | DAE Perspective | Experiment Setup, Time Channels: select a new time channel file | The current file updates when clicking Apply Changes | Pass |  | Bishal
6 | 15 |  | No | YES | DAE Perspective | Experiment Setup, Data Acquisition: select a new wiring/detector/spectra table file without clicking 'Apply changes' | The current table does not update | Pass |  | Bishal
6 | 16 |  | No | YES | DAE Perspective | Experiment Setup, Data Acquisition: select a new wiring/detector/spectra table file | The current table updates after clicking Apply Changes | Pass |  | Bishal
6 | 17 |  | No | YES | DAE Perspective | Experiment Setup, Periods: select select a new period file without clicking 'Apply changes' | The current file does not update | Pass |  | Bishal
6 | 18 |  | No | YES | DAE Perspective | Experiment Setup, Periods: select a new period file. | The current file updates after clicking Apply Changes | Pass |  | Bishal
6 | 19 |  | No | Difficult | DAE Perspective | Switch to spectra plots tab, attempt to change Y-axis type | Spectra plots appear. Y-axis change is reflected in the graph's Y axis. | Pass | No actual data available at time of testing so just checked that blank plots appear and that the Y axis label updates properly when changing axis type. | Bishal
6 | 20 |  | Yes | Yes | DAE Perspective | Experiment Setup, Periods: content of "Period Settings" group changes appropriately depending on "Period Type" Selection | Software: can only r/w number of software periods; Hardware Internal: Hardware period sequences, delay and period source; Hardware External: like hardware internal but with period sequences and frames parameter disabled | Pass |  | Bishal
6 | 21 |  | Yes | Yes | DAE Perspective | Experiment Setup, Periods: (only applicable for hardware period types) window shows appropriate controls depending on selected period source | "Specify Parameters" shows table with parameters, "Read from file" shows file selection drop down menu. | Pass |  | Bishal
6 | 22 |  | No | Yes | DAE Perspective | When you have no TCB files in your settings then the check the TCB file dropdown | Error message points to the correct location to place files | Pass |  | Bishal
6 | 23 |  | No | Yes | DAE Perspective | 6-22 for wiring tables | Error message points to the correct location to place files | Pass |  | Bishal
6 | 24 |  | No | Yes | DAE Perspective | 6-22 for detector tables | Error message points to the correct location to place files | Pass |  | Bishal
6 | 25 |  | No | Yes | DAE Perspective | 6-22 for spectra tables | Error message points to the correct location to place files | Pass |  | Bishal
6 | 26 |  | No | Yes | DAE Perspective | 6-22 for period files | Error message points to the correct location to place files | Pass |  | Bishal
6 | 27 |  | No | Yes | DAE Perspective | Create a block called [PVPREFIX]:DAE:TITLE:DISPLAY. Check its value when the "Show DAE title on web dashboard" box is ticked/unticked in the DAE run summary | Unticked: No. Ticked: Yes | Pass | Previously automated but system test became unstable | Bishal
7 | 1 |  | Yes | Yes | Experiment Details Perspective | Switch to Experiment Details Perspective | Successful | Pass |  | Adam
7 | 2 |  | No | Yes | Experiment Details Perspective | Set a RB number of an actual Experimental Team | Successful | pass |  | Bishal/Adam
7 | 3 |  | Yes | Yes | Experiment Details Perspective | Set a fake RB number | Successful | fail |  | Bishal/Adam | test worded wrongly? got message no users found and couldnt find any RB number
7 | 4 |  | No | Yes | Experiment Details Perspective | Search for an RB number by user's name | Successful | pass |  | Bishal/Adam
7 | 5 |  | Yes | Yes | Experiment Details Perspective | Alter the Team information | Successful | pass |  | Bishal/Adam
7 | 6 |  | No | Perhaps | Experiment Details Perspective | check parameters table | All entries in the Parameter tables are relevant and have name and units | Pass |  | Bishal
7 | 7 |  | No | No | Experiment Details Perspective (another client) | Open another client (client B) | Client opens and contains the same experimental details as in original client (client A) | Pass | Has failed in the past | Bishal
7 | 8 |  | No | Partial | Experiment Details Perspective | Alter the name information to include utf8 characters in the surname string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Name is utf8 string in both Users (in banner) and Table for both client A and B | Pass | Has failed in the past | Bishal
7 | 9 |  | No | Partial | Experiment Details Perspective | Alter the name information to include utf8 character in the forenames string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø surname" | Name is utf8 string in Table for both client A and B | Pass | Has failed in the past | Bishal
7 | 10 |  | No | Partial | Experiment Details Perspective | Alter the institute to include the utf8 characters "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Institute is utf8 string in Table for both client A and B | Pass | Has failed in the past | Bishal
8 | 1 |  | No | Yes | IOC log perspective | Select perspective | Opens when the button is selected | Pass |  | Adam
8 | 2 |  | No | Yes | IOC log perspective | Show info messages | Successful | Pass |  | Bishal
8 | 3 |  | No | Yes | IOC log perspective | Limit the messages to content value | Successful | Pass |  | Bishal
8 | 4 |  | No | Yes | IOC log perspective | Limit the messages to a date range | Successful | Pass |  | Bishal
8 | 5 |  | No | Yes | IOC log perspective | Limit the messages to a sender | Successful | Pass |  | Bishal
8 | 6 |  | No | Yes | IOC log perspective | Limit the messages to a sender host (the sender host column can be enabled by right clicking on the columns of the ioc log table) | Successful | Pass |  | Bishal
8 | 7 |  | No | Yes | IOC log perspective | Limit the messages to a severity | Successful | Pass |  | Bishal
8 | 8 |  | No | Yes | IOC log perspective | Limit the messages to a Type | Successful | Pass |  | Bishal
8 | 9 |  | No | Yes | IOC log perspective | Limit the messages to an Application ID (the Application ID column can be enabled by right clicking on the columns of the ioc log table) | Successful | Pass |  | Bishal
8 | 10 |  | No | Yes | IOC log perspective | Clear the search criteria, using X button next to search | Only the most recent log messages appear in table | Pass |  | Bishal
8 | 11 |  | No | Difficult | IOC log perspective | Switches correctly when instrument is switched | Log messages from the new instrument are now displayed | Pass |  | Bishal
8 | 12 |  | No | Yes | IOC log perspective | Use the message simulator (found int IOCLogServer->master->dev-tools) | Messages with higher severity than the filter are shown. | Pass |  | Bishal
8 | 13 | 1521 | No | No | IOC log perspective | Generate 150,000 and check gui works | Gui should remain responsive as messages are coming in. Last message should be displayed before new next info message appears. (i.e. the view is refreshed for the last message) | pass | The gui is filtering out requests to refresh the message view but this means the last refresh may not be caught hence the check on the last message. messages are not in order | Bishal/Adam
8 | 14 |  | partially | yes | Log plotter perspective | Select no blocks | Displays message explaining how to view block history | Pass |  | Bishal
8 | 15 |  | No |  | Log plotter perspective | Displays a block history (via the block menu) | block history correctly displays | Pass |  | Bishal
9 | 1 |  | Yes | Yes | Motors Perspective | Select perspective | Opens when the button is selected | Pass |  | Adam
9 | 2 |  | Yes | Yes | Motors Perspective | Switch between the tabs | Successful | Pass |  | Adam
9 | 3 |  | Yes | Yes | Motors Perspective | Check motors | Any running motor records are visible | Pass |  | Adam
9 | 4 |  | Yes | Yes | Motors Perspective | Double click a motor | Opens a motor OPI | Pass |  | Adam
9 | 5 |  | No | Yes | Motors Perspective | Open a motor OPI from the motors perspective. Switch instrument | The open OPI should close | Pass |  | Adam
10 | 1 |  | Yes | Yes | Scripting Perspective | Select perspective | Opens when the button is selected | Pass |  | Adam
10 | 2 |  | Yes | Yes | Scripting Perspective | Wait for console to load | Loads successfully, with EPICS/GeniePython support | Pass | Check if you can use g library by typing g. and seeing if you can select a function. Try importing inst | Adam | added more instruction
10 | 3 |  | Yes | Yes | Scripting Perspective | Read a block using cget in the scripting console | Value returned in dictionary | Pass | cget("BLOCK") and replace BLOCK with name of your block. See if all values match | Adam | added more instruction
10 | 4 |  | Yes | Yes | Scripting Perspective | Set a block in the scripting console | Value set | Pass | cset("BLOCK",AMOUNT) read more here: https://github.com/ISISComputingGroup/ibex_user_manual/wiki/genie_python-Commands | Adam | added more instruction
10 | 5 |  | Yes | Yes | Scripting Perspective | Read a block using cshow | Value returned as string with information after in brackets | Pass | cshow("BLOCK") | Adam | added more instruction
10 | 6 |  | Yes | Yes | Scripting Perspective | Read a disconnected block using cget | Value returned as None | Pass |  | Adam
10 | 7 |  | Yes | Yes | Scripting Perspective | Read a disconnected block with cshow | Value returned as "*** disconnected ***" | Pass |  | Adam
10 | 8 |  | Yes | Yes | Scripting Perspective | start a run from the scripting console | Run starts | Pass | g.begin() Refer to wiki if you encounter errors | Adam | added more instruction
10 | 9 |  | Yes | Yes | Scripting Perspective | end a run from the scripting console | Run ends | Pass | g.end() | Adam | added more instruction
10 | 10 |  | Yes | Yes | Scripting Perspective | pause a run from the scripting console (start first) | Run pauses | Pass | g.pause() | Adam | added more instruction
10 | 11 |  | Yes | Yes | Scripting Perspective | resume a run from the scripting console (pause first) | Run resumes | Pass | g.resume() | Adam | added more instruction
11 | 1 |  | Yes | Yes | Synoptic Perspective | Select perspective | Opens when the button is selected | Pass |  | Bishal
11 | 2 |  | Yes | Yes | Synoptic Perspective | Select a synoptic | Successful | Pass |  | Bishal
11 | 3 |  | Yes | Yes | Synoptic Perspective | Browse the synoptic navigation | Elements correctly display | Pass |  | Bishal
11 | 4 |  | Yes | Yes | Synoptic Perspective | Open an OPI (from a synoptic element) | OPI opens | Pass |  | Bishal
11 | 5 |  | No |  | OPIs | Open the HVCAEN OPI, attempt to edit the list of channels | Allows you to see and edit the list of channels you can have | Pass |  | Bishal
12 | 1 |  | Yes | Yes | Web Links Perspective | Switch to web links perspective | Links are displayed in perspective and work. | Pass |  | Adam
12 | 2 |  | No | No | Web Links Perspective | Click links on page | Links open the correct web pages | Pass | "Launch maintenance website" is linked to instrument name and will 404 on dev instruments | Adam
13 | 1 |  | Yes | Yes | Switch Instruments | Switch instruments by typing a known name | Correctly switches | Pass |  | Adam
13 | 2 |  | Yes | Yes | Switch Instruments | Switch instruments by typing an unknown name and giving it the correct prefix | Correctly switches | Pass | Should probably remain in the manual tests until there is away to check the client pv prefix (#2419) | Bishal
14 | 0 |  | No | No | Configs | Open the java visual VM in C:\Program Files (x86)\Java\jdk<version>\bin\jvisualvm.exe and point it at the IBEX GUI. Keep it open through all the system tests to do with configurations. | This is not a test in itself, but will be necessary for test 15-59 later on!
14 | 1 |  | No | Yes | Configs | Edit the current config (add an IOC), and save it | changes stored | Pass |  | Adam
14 | 2 |  | No | Yes | Configs | Edit the current config by adding an IOC and cancel the dialog | No new IOCs are started and no new IOCs have been added when you look in the edit config window again | pass |  | Adam
14 | 3 |  | No | Yes | Configs | Edit the current config (add a block), and save it | changes stored | pass |  | Adam
14 | 4 |  | No | Yes | Configs | Edit the current config by adding a block and cancel the dialog | No new bloxks appear in the block view and no new blocks have been added when you look in the edit config window again | pass |  | Adam
14 | 5 |  | No | Yes | Configs | Edit the current config (add a group), and save it | changes stored | pass |  | Adam
14 | 6 |  | No | Yes | Configs | Edit the current config by adding a group and cancel the dialog | No new groups appear in the block view and no new groups have been added when you look in the edit config window again | pass |  | Adam
14 | 7 |  | No | Yes | Configs | Edit the current config (select a component), and save it | changes stored | pass |  | Adam
14 | 8 |  | No | Yes | Configs | Edit the current config by adding a component and cancel the dialog | No new components have been added when you look in the edit config window again | pass |  | Adam
14 | 9 |  | No | Yes | Configs | Edit the current config (set IOC macro), and save it. | Changes stored and applied at the IOC level | pass |  | Adam | tested with GALIL switched motor control from 01 to 02 and it used MTR0201 after that
14 | 10 |  | No | Yes | Configs | Edit the current config by setting an IOC macro and cancel | The IOC macro has not changed in the IOC level and does not appear changed when the config is editted again | pass |  | Adam
14 | 11 |  | No | Yes | Configs | Create a new config. Click 'Save As'. Enter the name of the current configuration. | An error message appears saying the operation is invalid and the 'OK' button remains disabled. | pass | There should be error saying "Name matches the current configuration" | Adam | added more instruction
14 | 12 |  | No | Yes | Configs | Create a new config. Click save. Enter the name of another configuration. | When you click ok, a confirmation box appears asking whether you want to overwrite the existing configuration. | pass |  | Adam
14 | 13 |  | No | Yes | Configs | Edit a config (not current) by setting some IOC macros. Load the config. | The new macro values are displayed in the config and they are applied to the respective IOCs | pass |  | Adam | in new configuration brought back GALIL to 01 (see test 9 in this section)
14 | 14 |  | No | Yes | Configs | Edit the current config (IOC PV values), and save it. | changes stored | pass |  | Adam
14 | 15 |  | No | Yes | Configs | Edit the current config (IOC PV values) and cancel | no changes seen | pass |  | Adam
14 | 16 |  | No | Yes | Configs | Edit the current config (summary: description and synoptic), and save it | changes stored | pass |  | Adam
14 | 17 |  | No | Yes | Configs | Edit the current config and cancel (summary: description and synoptic) | no changes seen | pass |  | Adam
14 | 18 |  | No | Yes | Configs | Edit an existing config, and save it | changes stored | pass |  | Adam
14 | 19 |  | No | Yes | Configs | Create a new config, and save it | changes stored | pass |  | Adam
14 | 20 |  | No | Yes | Configs | Delete a config | Config deletes | pass |  | Adam
14 | 21 |  | No | Yes | Configs | Delete multiple configs simultaneously | Configs delete | pass |  | Adam
14 | 22 |  | No | Yes | Configs | Load a config | Configs load | pass |  | Adam
14 | 23 |  | No | Yes | Configs | Create a new config and save as component | Component saves | pass |  | Adam
14 | 24 |  | No | Yes | Configs | Create a new component | Component created | pass |  | Adam
14 | 25 |  | No | Yes | Configs | Edit a component | Component updates | pass |  | Adam
14 | 26 |  | No | Yes | Configs | Delete a component | Component deletes | pass |  | Adam
14 | 27 |  | No | Yes | Configs | Add a block, verifying that the PV search works | Block added, PV search successful | pass |  | Adam | It took a while for PV to be picked up in blocks section
14 | 28 |  | No | Yes | Configs | Edit a block | Block updates | pass |  | Adam
14 | 29 |  | No | Yes | Configs | Delete a block | Block deletes | pass |  | Adam
14 | 30 |  | No | Yes | Configs | A block can be created with run control | Block created | pass |  | Adam | created by going run control -> edit host configuration -> add block
14 | 31 |  | No | Yes | Configs | Check new block log settings | Settings default to enabled and 30 s rate of periodic scan | pass |  | Adam
14 | 32 |  | No | Yes | Configs | A block can be created with logging enabled | Block created | pass |  | Adam/ Bishal | Not sure what this means -Adam
14 | 33 |  | No | Yes | Configs | Run control can be turned off for a block | Run control turns off | pass |  | Adam
14 | 34 |  | No | Yes | Configs | Logging can be turned off for a block | Logging turns off | fail | Still logging in C:\Instrument\Var\logs\gateway\blockserver | Bishal
14 | 35 |  | No | Yes | Configs | Run control can be reinstated for a block via the config editor | Run control reinstated | pass |  | Bishal
14 | 36 |  | No | Yes | Configs | Logging can be reinstated for a block via the config editor | Logging reinstated | pass |  | Bishal
14 | 37 |  | Yes | Yes | Configs | Add a group | group added | pass |  | Adam
14 | 38 |  | Yes | Yes | Configs | Add blocks to the group | blocks added | pass |  | Adam
14 | 39 |  | No | Yes | Configs | Remove blocks from the group | blocks removed | pass |  | Adam
14 | 40 |  | No | Yes | Configs | Remove a group | group removed | pass |  | Adam
14 | 41 |  | Yes | Yes | Configs | Add components to the config | components added | pass |  | Adam | these tests were already done as part of previous tests, perhaps redundant (see test 8)
14 | 42 |  | Yes | Yes | Configs | Remove components from the config | components removed | pass |  | Adam
14 | 43 |  | No | Yes | Configs | Add some values to the IOC macros | values added | pass |  | Adam
14 | 44 |  | No | Yes | Configs | Add a default synoptic to a config | Default synoptic added | pass |  | Adam
14 | 45 |  | No | Yes | Configs | Edit the default synoptic of a config | Default synoptic edited | pass |  | Adam
14 | 46 |  | No | Yes | Configs | Remove the default synoptic of a config | default synoptic removed | pass |  | Adam
14 | 47 |  | No | No | Configs | All configs can be viewed via their config name PV from a remote system. Example on NDXIRISTEST: 1. Run caget -S -t IN:IRISTEST:CS:BLOCKSERVER:CONFIGS ¦ uzhex 2. Find the PV for the config you want to view 3. Run caget -S -t IN:IRISTEST:CS:BLOCKSERVER:<>:GET_CONFIG_DETAILS ¦ uzhex | Successful | pass |  | Bishal
14 | 48 |  | No | Yes | Configs | Create a block with a pv which has a field (VAL, HLM on a motor) | Block creates with correct PV | pass |  | Adam | created block for TE:NDW1798:MOT:MTR0101, confirmed that it connects to recsim GALIL01
14 | 49 |  | No | Yes | Configs within the system | Set 1 IOCs to Auto Start, 1 IOC Auto restart, 1 IOC to both, 1 IOC to neither in a config. Load that config. | The two IOCs with Auto Start set have started. | pass |  | Adam
14 | 50 |  | No | Yes | Configs within the system | Edit a component of the current config, get an idea of length of time for config to reload | takes <10s | pass |  | Adam
14 | 51 |  | No |  | Configs within the system | Set a macro via the GUI | Macro set | pass |  | Bishal
14 | 52 |  | No | No | Configs within the system | Verify that config changes are pushed to the repo (changes are only passed once per 5 minutes) | changes passed | pass |  | Bishal
14 | 53 |  | No | Yes | Configs within the system | Reload the config whilst an IOC not in the config is running (can be done via genie python g.reload_current_config()) | IOC stops | pass |  | Bishal
14 | 54 |  | No | Yes | Configs | Create a new configuration. Click `save as`. Try adding spaces (start, middle and end of name) and special characters. | Error appears and config cannot be saved | pass |  | Adam
14 | 55 |  | No | Yes | Configs | 1. Create a configuration. Add an IOC. Set it to auto-start and put it in recsim mode. Save the config. 2. Edit the config, change the sim level to None. Save the config. | 1. Verify the IOC starts. 2. Verify that the Block Server restarts the IOC | pass | you can easily notice IOC restarting in console (see test 2 section 1) | Adam | added more instruction
14 | 56 |  | No | Yes | Configs | Create a config with an 2 IOCs in. Load it Remove an ioc and add a different IOC | config has the correct IOCs in it | pass |  | Adam
14 | 57 |  | No | Yes | Configs | Add an IOC with custom settings (e.g. recsim) to a component Add the component to a config Load the config and run the IOC | It has the settings set in component | pass | trying to change recsim should be greyed out in configuration menu as its part of component | Adam | added more instruction
14 | 58 |  | No | Yes | Configs | Create a configuration. Set a default synoptic and save | previously selected synoptic is set as this configuration's default synoptic | pass | Verify this works when the default synoptic of the configuration being edited is different from the default | Adam
14 | 59 |  | No | Yes | Configs | Create a synoptic. Create a new configuration with that synoptic as default. Save. Delete the synoptic | The synoptic will be deleted and no IOC error will be generated | pass | You should get a warning for this | Adam | added more instruction
14 | 60 |  | No | Yes | Configs | Change the description in the current config, save. | Gateway, Runcontrol, Archiver and IOCs don't restart. | pass |  | Bishal
14 | 61 |  | No | Yes | Configs | Change blocks in the current config, save. | Gateway, Runcontrol, and Archiver restart. | pass |  | Bishal
14 | 62 |  | No | No | Configs | After doing all of the above system tests, check that memory usage is not excessive. This can be done using the java visual VM which was opened in 14-0. Click here for detailed instructions | While doing all the 14-x tests, memory usage should be fluctuating between 100 and 200MB on average, with no upward trend over a long time period (fluctuations are normal). |  |  |  | I created a screenshot of results since I figured someone might find this helpful/interesting. See https://stfc365.sharepoint.com/sites/IBEX/Shared%20Documents/technical/VisualVMgraphsRelease800_29_07_2021.png It seems to me like a slight rise in memory usage but not concerning -Adam
15 | 1 |  | Yes | Yes | Synoptics | Create a synoptic | Synoptic created | pass |  | Adam
15 | 2 |  | Yes | Yes | Synoptics | Edit a synoptic | Synoptic edited | pass |  | Adam
15 | 3 |  | Yes | Yes | Synoptics | Delete a synoptic | Synoptic deleted | pass |  | Adam
15 | 4 |  | Yes | Yes | Synoptics | Add a component to a synoptic | Component added | pass |  | Adam
15 | 5 |  | Yes | Yes | Synoptics | Delete a component from a synoptic | Component deletes | pass |  | Adam
15 | 6 |  | Yes | Yes | Synoptics | Copy a component on a synoptic | Component copies | pass |  | Adam
15 | 7 |  | Yes | Yes | Synoptics | Delete multiple components from a synoptic | Components delete | pass |  | Adam
15 | 8 |  | Yes | Yes | Synoptics | Copy multiple components on a synoptic (Note: Not the components as in sub-config) | Components copy | pass |  | Adam
15 | 9 |  | No | Yes | Synoptics | Add a component and select a target (e.g. Analyser) | Appropriate target details come up | pass |  | Adam
15 | 10 |  | No | Yes | Synoptics | Using the Analyser*, alter the component target details to be something else(*or whichever you picked in the previous test) | Details change | pass |  | Adam
15 | 11 |  | No | Yes | Synoptics | Confirm you can set a custom icon on the Analyser*, which persists when you change the target. Confirm this persists after saving and reopening the dialog. | Successful | pass |  | Adam
15 | 12 |  | No | Yes | Synoptics | On the Analyser*, confirm the "Clear" button works (i.e. resets to an undefined component) and that subsequently selecting a target sets the correct default icon. | Successful | pass |  | Adam
15 | 13 |  | Yes | Yes | Synoptics | Attempt to create a synoptic with a name of greater than 30 characters | Error appears and synoptic cannot be saved | pass |  | Adam
15 | 14 |  | No | Yes | Synoptics | Add a new PV to a component | PV receives a default name that is unique (for that component) | pass |  | Adam
15 | 15 |  | No | Yes | Synoptics | Attempt to add multiple components with the same name to a synoptic | Error appears and synoptic cannot be saved | pass | can still preview synoptic | Adam
15 | 16 |  | No | Perhaps | Synoptics | All synoptics can be loaded on a remote instrument (especially synoptics with lots of components) | Synoptics load | pass |  | Bishal/Adam
15 | 17 |  | No | Yes | Synoptics within the system | Create a synoptic that shows the beam, load it | beam is present | pass |  | Bishal/Adam
15 | 18 |  | No | Yes | Synoptics within the system | Create a synoptic that doesn't show the beam, load it | beam is not present | pass |  | Bishal/Adam
15 | 19 |  | No | Yes | Synoptics within the system | Once synoptic is saved it is available immediately in the drop down in the synoptic perspective | The synoptic is available immediately | pass |  | Adam
15 | 20 |  | No | Yes | Synoptics within the system | A synoptic can be edited after saving using "save as" | Synoptic editable | pass |  | Adam
15 | 21 |  | No | Yes | Synoptics within the system | Add a component to a synoptic. Change its type at least twice. | Each time the target details switch to the default for the selected type | pass |  | Adam
15 | 22 |  | No | Yes | Synoptics | Open the Synoptic perspective. Check synoptic selected in drop-down | synoptic selected by default is the current configuration's default synoptic | pass |  | Adam
15 | 23 |  | No | Yes | Synoptics | With the synoptic perspective open, switch configurations | new configuration's default synoptic automatically brought up | pass |  | Adam
15 | 24 |  | No | Yes | Synoptics | In the synoptic perspective,push the load default button | Current configuration default synoptic selected in the drop-down | pass |  | Adam
16 | 1 |  | Yes | Yes | IOC Start/Stop | Start an IOC from the menu | IOC starts | Pass |  | Adam
16 | 2 |  | No | Yes | IOC Start/Stop | Using the console, stop an IOC set to auto-restart in the config. | IOC stops | Pass | Should restart after a moment | Adam | added more instruction
16 | 3 |  | Yes | Yes | IOC Start/Stop | Stop an IOC | IOC stops | Pass |  | Adam
16 | 4 |  | No | Yes | IOC Start/Stop | Press the "Restart" button in the start/stop IOC dialog both for IOC with and without "auto-restart" enabled. | IOC restarts | Pass |  | Adam
16 | 5 | 3795 | No | Yes | IOC Start/Stop | Add the Simple IOC to a test configuration with Auto-start and auto-restart ticked. Boot the Simple IOC. From an epics terminal issue the command `caput %MYPVPREFIX%SIMPLE:CRASHVALUE 1` to crash the IOC | The IOC should reboot. You shouldn't be prompted to debug the crashed IOC. | Pass |  | Adam
17 | 1 |  | Yes | Yes | Run Control | View the run control settings | Run control window opens | Pass |  | Adam
17 | 2 |  | Yes | Yes | Run Control | Edit the run control settings | Run controls edit correctly | Pass |  | Adam
17 | 3 |  | Yes | Yes | Run Control | Restore the configuration values for run control | values restore | Pass |  | Adam
18 | 1 |  | No | Yes | OPIs and IOCs | With an IOC started, open OPI, get an idea of length of time before blocks are connected | Pass at <5 seconds | Pass |  | Bishal
18 | 2 |  | No | Yes | OPIs and IOCs | With an OPI open , Start IOC, get an idea of length of time before pvs are connected | pass at <5s | Pass | Typically in the region 60s for immediate and 5 mins for switch off for 2; and 2:30 for connect ioc after OPI is open | Bishal
18 | 3 |  | No | Yes | OPIs and IOCs | Start IOC, open OPI, Restart IOC, get an idea of length of time | Pass at <5 seconds | Pass |  | Bishal
18 | 4 |  | No | Yes | OPIs and IOCs | Start IOC, open OPI, Stop IOC, Wait 2 minutes, Restart IOC, get an idea of length of time before pvs reconnect | pass at <60 seconds | Pass |  | Bishal
18 | 5 |  | No | Yes | OPIs and IOCs | Open OPI, Wait 2 minutes, Start IOC, get an idea of length of time | pass at <5 seconds | Pass |  | Bishal
19 | 1 |  | No | Perhaps | Motors | Create blocks looking at motors, and vary the run control limits | violations change | Pass |  | Bishal
19 | 2 |  | No | Perhaps | Motors | In a scripting window run the two commands waitfor_move("motor1", "motor2") to check when the motors stop. Also run check_limit_violations("motor1", "motor2") to see soft limit violations within the motor | Motors stop at correct points | Pass |  | Bishal
20 | 1 |  | Yes | Yes | Blocks | Create a block | Block appears in the blocks panel | Pass |  | Adam
20 | 2 |  | No | Yes | Blocks | Disconnect a connected block | appears disconnected within 5s | Pass |  | Bishal
20 | 3 |  | No | Yes | Blocks | Reconnect a disconnected block (check various disconnection times up to 5mins) | appears connected within 10-20s | Pass |  | Bishal
20 | 4 |  | No | Yes | Blocks | Start up SIMPLE IOC and put a block on VALUE1. Write a 4 into the PV to cause a MINOR-alarm state | Orange border around block | Pass |  | Bishal
20 | 5 |  | Yes | Yes | Blocks | Take a block under run control and remove run control. | Run control icon disappears | Pass |  | Bishal
20 | 6 |  | No | Yes | Blocks | Write a 1 to the VALUE1 PV to cause a MAJOR alarm. | Red border around block | Pass |  | Bishal
20 | 7 |  | Yes | Yes | Blocks | Block pointing at ai: 0 is displayed as 0.000 (PREC 3) and 0.00000 (PREC 5) |  | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 8 |  | No | Yes | Blocks | Put block into an INVALID-alarm state (.SEVR field) | Purple border appears around block | Pass |  | Bishal
20 | 9 |  | Yes | Yes | Blocks | Block pointing at ai: 0.1 is displayed as 0.100 (PREC 3) and 0.10000 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 10 |  | Yes | Yes | Blocks | Block pointing at ai: 0.01 is displayed as 0.010 (PREC 3) and 0.01000 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 11 |  | Yes | Yes | Blocks | Block pointing at ai: 0.001 is displayed as 0.001 (PREC 3) and 0.00100 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 12 |  | Yes | Yes | Blocks | Block pointing at ai: -0.001 is displayed as -0.001 (PREC 3) and -0.00100 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 13 |  | Yes | Yes | Blocks | Block pointing at ai: 0.001234 is displayed as 0.001 (PREC 3) and 0.00123 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 14 |  | Yes | Yes | Blocks | Block pointing at ai: -0.001234 is displayed as -0.001 (PREC 3) and -0.00123 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 15 |  | Yes | Yes | Blocks | Block pointing at ai: 0.0009 is displayed as 9.000E-5 (PREC 3) and 9.00000E-5 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 16 |  | Yes | Yes | Blocks | Block pointing at ai: -0.0009 is displayed as -9.000E-5 (PREC 3) and -9.00000E-5 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 17 |  | Yes | Yes | Blocks | Block pointing at ai: 15 is displayed as 15.000 (PREC 3) and 15.00000 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 18 |  | Yes | Yes | Blocks | Block pointing at ai: 999999 is displayed as 999999.000 (PREC 3) and 999999.00000 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 19 |  | Yes | Yes | Blocks | Block pointing at ai: -999999 is displayed as -999999.000 (PREC 3) and -999999.00000 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 20 |  | Yes | Yes | Blocks | Block pointing at ai: 1000000 is displayed as 1.000E6 (PREC 3) and 1.00000E6 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 21 |  | Yes | Yes | Blocks | Block pointing at ai: -1000000 is displayed as -1.000E6 (PREC 3) and -1.00000E6 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 22 |  | Yes | Yes | Blocks | Block pointing at ai: 1234567 is displayed as 1.235E6 (PREC 3) and 1.23457E7 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 23 |  | Yes | Yes | Blocks | Block pointing at ai: -1234567 is displayed as -1.235E6 (PREC 3) and -1.23457E7 (PREC 5) | displays correctly | Pass | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG | Bishal
20 | 24 |  | Yes | Yes | Blocks | Block pointing at longin: never displayed as scientific notation using the following script: from time import sleep for val in [0, 15, 999999, 1000000, 1234567]: g.cset(b.LONG_VAL, val) sleep(0.5) g.cset(b.LONG_VAL, -val) sleep(0.5) | displays correctly | Pass | Can use the LONG PVs from SIMPLE IOC connected to a block called LONG_VAL | Bishal
20 | 25 |  | Yes | Yes | Blocks | Create a block. Right click on it in the blocks dashboard and select `Edit host configuration`. Change the block. Click cancel. | Changes are not applied | Pass |  | Adam
20 | 26 |  | Yes | Yes | Blocks | Create a block. Right click on it in the blocks dashboard and select `Edit host configuration`. Change the block. Click ok. | Changes are applied | Pass |  | Adam
20 | 27 |  | No | Yes | Blocks | Create a hidden block. Right click on any group and confirm that you can switch between showing and hiding the block. | Can show/hide block | Pass |  | Adam | Removed duplacate test here
20 | 28 | 1672 | Yes | Yes | Groups | Create a group containing ONLY hidden blocks. | Group is NOT shown, except when the right-click option "Shown hidden blocks" is selected | Pass |  | Adam
21 | 1 |  | No | Yes | Instrument List | Open instrument list (IBEX > Switch instrument) | List of supported instruments appears in the instrument list | Pass |  | Adam | List is populated but not sure if it contains all of instruments its supposed to contain
21 | 2 |  | No | Yes | Instrument List | When on an instrument machine for an instrument in CS:INSTLIST, open the instrument list. | The instrument name only appears once and it is at the top of the list | Pass |  | Adam
21 | 3 |  | No | Perhaps | Instrument List | On a developer machine, open the instrument list | Local host name appears at the top of the instrument list | Pass |  | Adam
21 | 4 |  | No | Yes | Instrument List | Can switch from local host to other instrument | Successful | Pass |  | Adam
21 | 5 |  | No | Yes | Instrument List | Can switch between two listed instruments | Successful | Pass |  | Adam
21 | 6 |  | No | Yes | Instrument List | Can switch to a custom instrument not on the list | Successful | pass | Can connect to machines on R3, R80, R55 networks. | Adam/Bishal
22 | 1 |  | No | No | Config Version Control | On a branch named after your system, create new configurations. | New configurations get added to the local repository (after 300 seconds) | pass |  | Bishal
22 | 2 |  | No | No | Config Version Control | On a branch named after your system, change a configuration. | Config changes get committed to the local repository (after 300 seconds) | pass |  | Bishal
22 | 3 |  | No | No | Config Version Control | On a branch named after your system, change a configuration. | Config changes get pushed to a remote repository (after 300 seconds) | pass |  | Bishal
22 | 4 |  | No | No | Config Version Control | On a branch starting with ND that is not your system name, change a config | Config changes do not get committed or pushed (after 300 seconds) | pass |  | Bishal
22 | 5 |  | No | No | Config Version Control | Create a config starting with rcptt_ | config not added to a repo | pass | Should be made clear if this test should be done in the same config branch as the machine's name | Bishal
22 | 6 |  | No | No | Config Version Control | Create a synoptic starting with rcptt_ | synoptic not added to a repo | pass |  | Bishal
23 | 1 |  | No | No | Read-only access | Right-click edit block whilst on a read-only instrument | option not available | pass | Gives an error window | Bishal
25 | 1 |  | No | Yes | genie_python | While the DAE is in a state it can begin a run: Clone the developers manual wiki and load the script "genie_python_dae.py" found and in the testing folder from the scripting perspective using g.load_script(<script_name>). Run script | No assertions are violated | pass | you need to use: git clone https://github.com/ISISComputingGroup/ibex_developers_manual.wiki.git At the end it should say TESTS COMPLETED SUCCESSFULLY | Adam | added more instruction I needed to add argument check_script=False or else I was getting error 'g is undefined'
25 | 2 |  | No | Yes | genie_python | test 25-1 in a genie_python console | No assertions are violated | pass |  | Adam
25 | 3 |  | No | Yes | genie_python | Create a config with SIMPLE IOC and blocks TEST_BLOCK_NUM (SIMPLE:VALUE:P5) and TEST_BLOCK_STR (SIMPLE:HELLO). Run the SIMPLE IOC. Run script "genie_python_blocks.py" from the testing area of the developer manual. | No assertions are violated | pass |  | Adam
25 | 4 |  | No | Yes | genie_python | test 25-3 in a genie_python console | No assertions are violated | pass |  | Adam
25 | 5 |  | No | No | genie_python | From a genie_python console (i.e. from the GUI) run `g.plot_spectrum(1)` | A matplotlib window should appear with a sensible plot (probably a flat line for a simulated instrument). No error message should appear in the scripting window. Make sure the default size of the window is sensible, such as half of the size of the scripting window. | pass |  | Adam
26 | 1 |  | No | Yes | Device screen | Add a device screen and select 'Remove this device when IBEX is closed'. Restart the client | Device screen is removed from device screens list after restart | Pass | Previously automated but system test became unstable | Adam
26 | 2 |  | Yes | Yes | Device Screens | Attempt to add/edit/delete Device Screens | Successful | Pass |  | Adam
26 | 3 |  | No | Yes | Device screen | Add a device screen and select 'save this device screen'. Restart the client | Device screen is preserved on the device screens list after restart | Pass |  | Adam
26 | 4 |  | Yes | Yes | Device Screens | Confirm that device screens can not be saved if one or more items is not pointing at a target OPI. | If target is blank: Error message is shown naming the offending device screen & ok button is disabled | Pass |  | Adam
27 | 1 |  | No | Perhaps | Preferences | Open the GUI without opening the motors perspective. Change the colour scheme in the Preferences menu. | The table of motors colours background has changed. | Pass |  | Adam
27 | 2 |  | No | Perhaps | Preferences | With the motors perspective open, change the colour scheme in the Preferences menu. | The table of motors colours background has changed. | Pass |  | Adam
29 | 1 | 3213 | No | Yes | Menu items | Verify that the manager mode dialog can be opened first time. From GUI go to IBEX menu -> Manager mode. | The dialog should either ask you for a password if you aren't in manager mode already, or ask you if you want to leave manager mode if you were. | Pass | The password is reliablebeam | Adam
29 | 2 |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission for (or is offline) open the synoptic menu | All items are greyed out | Pass |  | Bishal
29 | 3 |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission open the Configuration submenu items | Edit item is now called view | Pass |  | Bishal
29 | 4 |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission look at the top item of the Configurations menu | Top item is not edit current config but is view current config | Pass | This one and above could be the same step | Bishal
29 | 5 |  | No | No | Menu items | Check that you can login to "manager mode" with the instrument scientist password. (Ibex menu -> manager mode). | Check that the banner item indicates that you have successfully entered manager mode (you should see "manager mode: active" in red). | Pass | Cannot be automated because this test uses a password. | Bishal
29 | 6 |  | No | No | Menu items | Check that you can log out from "manager mode" after performing the above test. | "manager mode: No "in black | Pass |  | Bishal
30 | 1 |  | No | Yes | JournalViewer | Check the JournalViewer can establish a connection to the database | Status at the bottom shows last refresh time | Pass |  | Bishal
30 | 2 |  | No | No | JournalViewer | Check the JournalViewer handles failure to establish a connection properly. Change to a nonsense machine (e.g. abcdedg). | Status at the bottom shows highlighted error message in red. | Pass |  | Bishal
30 | 3 |  | No | No | JournalViewer | Confirm the manual "Refresh" button works. | Viewer refreshed | Pass |  | Bishal
31 | 1 | 3503 | No | Difficult | Layouts | `-modify your current layout - press "reset layout" - confirm that the layout resets to default | the layout resets to default | Pass |  | Bishal/Adam
32 | 1 |  | No | Difficult | Refl IOC | Change the Theta parameter and click move in refl opi | Putlog contains change to theta parameter number and move parameter | Pass |  | Bishal/Adam
33 | 1 | 5090 | Yes | Yes | Script Generator | Add some actions and then switch between script definitions | Help text should change. Actions should be removed on switching. The validity checks button should be disabled and generate script button should be enabled. | fail | Need to remove perspective form hidden perspectives in plugin_customizations.ini. Need script definitions from ScriptGeneratorConfig repository (best to use TestBranch) | Adam | there is no validity checks button anywhere, the rest passes
33 | 2 | 5090 | Yes | Yes | Script Generator | Add an action then duplicate it. Edit the contents of the first action to be valid and the contents of the second action to be invalid with different values. After checking the expected outcome, delete one of the actions. | Contents of actions should be different. The first action should be valid, the second should not be. After deleting, check that only one action has been deleted and the contents of the other remain the same. | pass | Same as above. | Adam
33 | 3 | 5090 | Yes | Yes | Script Generator | Add an action and make it valid, then duplicate it. The validity column should have a tick and be green. Click the generate script button. | A message box should appear. If you click the open file button it should open your file in notepad++. | pass | Same as above. Option to open file is only available when using save as It will say "failed to find notepad to launch" on clean virtual machine (no notepad++ installed) | Adam | added more comment should create ticket
33 | 4 | 5090 | Yes | Yes | Script Generator | Add a couple of actions and make them invalid. | The row should be coloured red and the validity column should have a cross in. The generate script button should be disabled. The get validity errors button should be enabled. When you hover over the actions they should give a reason they are invalid in the tooltip | fail | Same as above. | Adam | I didnt see anywhere "get validity errors" button
33 | 5 | 5090 | No | No | Script Generator | Wait for the open manual button to become enabled (shouldn't take more than a couple of seconds). Click the open manual button. | This should launch your browser and either take you to the using the script generator page on shadow or github. | pass | Same as above. Not made automated because it just becomes a nagios for the speed of shadow and/or github. | Adam
33 | 6 | 5090 | Yes | Yes | Script Generator | Add 3 actions, make one of them valid and duplicate it. Edit the contents of the duplicated action and one of the invalid actions. Move the actions up and down in the table. | The actions should move up and down and maintain their contents and validity as they do. | pass | Same as above. | Adam
33 | 7 | 5090 | No | Difficult | Script Generator | Add a few actions and have a general play around with moving them about and changing their contents. In task manager kill Python. Then continue playing around. | The script generator should clear and display a reloading screen. This reloading screen should take a few seconds and then the table and buttons etc. should be displayed again. The contents of the table should have maintained their state before python was killed. | fail | Same as above. Run through GUI: The contents are maintained but script generator doesnt display any loading screen Standalone: Stuck on Reloading screen | Adam | The contents are maintained but script generator doesnt display any loading screen
34 | 1 | 5750 | No | Yes | Disabled GUI tests | In the GUI repository, look for any disabled tests in https://github.com/ISISComputingGroup/ibex_gui/blob/master/base/uk.ac.stfc.isis.ibex.client.tycho.parent/pom.xml and run them manually from eclipse by right clicking on the test project and saying run as -> junit test | All tests which are disabled in maven should pass when manually running them from eclipse. | N/A | Didnt find any disabled tests | Adam/Bishal

## Bugs
Bug Number | Fix, Ticket Ignore | Ticket Number (when added to git) | Title | From Test | Description (Description of what is wrong) | Steps to Reproduce
1 |  |  |  | section 33 test 1, 4 | There is no dedicated button "get validity errors" | add invalid action and have a look for button called "get validity errors"
2 | https://github.com/ISISComputingGroup/IBEX/issues/6690 https://github.com/ISISComputingGroup/IBEX/issues/6691 | 6690, 6691 |  | section 33 test 7 | Run through GUI: After deleting all Python processes in task manager, the script generator did keep its state but there was no loading screen Run standalone: After deleting Python nothing initially happens until you start to use script generator, then Reloading shows up and it gets stuck like this. | Open script generator, add some actions, make some of them invalid, move them around and play around a bit, open task manager, sort by name, delete all Python processes at once, pay attention to script generator to see if it shows loading screen
3 |  |  |  | section 7 test 3 | Test could be worded wrongly, got message no users found and couldnt find any RB number
4 | https://github.com/ISISComputingGroup/IBEX/issues/6692 | 6692 |  | section 33 test 3 | When run on clean virtual machine (standalone) then after clicking "save as" and selecting to show the script, it will say that "failed to find notepad to launch". Technically it's correct since VM didnt have notepad++ installed which test is asking for but perhaps something should be done to inform user or maybe even allow normal notepad to be used instead in that case | Run on clean virtual machine with no Notepad++ installed: Open script generator, add some actions, click save as, click yes to show script
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25