## Cannot be automated tests
section no | test number | Test Number | Relates to Ticket# | Relates to Footrpints ID | Is automated | Could be automated | Brief description of task/issue/function | Brief description of test | Expected Outcome | Pass/Fail | Comments
1 | 3 | 1-3 |  |  |  |  | The server starts in an appropriate way | Check EXPDB runs when IBEX server starts. | EXPDB runs when IBEX server starts. | PASS | Check experiment details search is populated, check log file for errors
1 | 4 | 1-4 |  |  |  |  | The server starts in an appropriate way | Check DBSVR runs when IBEX server starts. | DBSVR runs when IBEX server starts. | PASS | Check start/ stop ioc dialog is populated, check log file for errors
1 | 6 | 1-6 |  |  |  |  | The server starts in an appropriate way | Check PSCTRL runs when IBEX server starts. | PSCTRL runs when IBEX server starts. | PASS | Check start/stop ioc functionality works
1 | 7 | 1-7 |  |  |  |  | The server starts in an appropriate way | Check IOCLOG runs when IBEX server starts. | IOCLOG runs when IBEX server starts. | PASS | Check messages appear in GUI IOC log, check log file for errors
1 | 8 | 1-8 |  |  |  |  | The server starts in an appropriate way | Check JMS runs when IBEX server starts. | JMS runs when IBEX server starts. | PASS
1 | 9 | 1-9 |  |  |  |  | The server starts in an appropriate way | Check RUNCTRL_01 runs when IBEX server starts. | RUNCTRL_01 runs when IBEX server starts. | PASS
1 | 10 | 1-10 |  |  |  | No | The server starts in an appropriate way | Local console works |  | PASS
1 | 11 | 1-11 |  |  |  | No | The server starts in an appropriate way | Remote console works (e.g. console -M NDXDEMO -l spudulike EUROTHRM_01) (flag is a lower case L) |  | PASS
2 | 1 | 2-1 |  |  |  | No | GeniePython is working | Using a shortcut open GeniePython (In theory C:\Instrument\Apps\Python\genie_python should havea shortcut pointing to it. If not, simply run that script directly) |  | PASS
2 | 2 | 2-2 |  |  |  | No | GeniePython is working | Using a python command window import GeniePython (run config_env.bat, then open python. In python: from genie_python.genie_startup import *) |  | PASS
3 | 2 | 3-2 |  |  |  | No | The GUI start in an appropriate way | help/about in GUI is expected values (double-check with Jenkins build/commit numbers and java version) |  | PASS
3 | 5 | 3-5 |  |  |  | No | Blocks Perspective | Make sure there are no half visible blocks |  | PASS
3 | 6 | 3-6 |  |  |  |  | Buttons perspective is working | Check button behaviour on alarms button (flashing if there is an alarm, steady red if alarm has been viewed) |  | PASS
3 | 8 | 3-8 |  |  |  | Perhaps | Buttons perspective is working | Check button behaviour on IOC Log button (flashing red if there is an alarm, clears to grey on click) |  | PASS
4 | 2 | 4-2 |  |  |  | Perhaps | Alarms Perspective | Displays an appropriate tree of alarms |  | PASS
6 | 22 | 6-22 |  |  |  | No | DAE Perspective | Spectra Plots: Check that setting the spectra / period number updates the plot on a running instrument (Can use simluated DAE) |  | PASS
7 | 6 | 7-6 |  |  |  | Perhaps | Experiment Details Perspective | All entries in the Parameter tables are relevant and have name and units |  | PASS
7 | 7 | 7-7 |  |  |  | No | Experiment Details Perspective (another client) | Open another client (client B) | Client opens and contains the same experimental details as in original client (client A) | PASS | Has failed in the past
7 | 9 | 7-9 |  |  |  | Partial | Experiment Details Perspective | Alter the name information to include utf8 characters in the surname string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Name is utf8 string in both Users (in banner) and Table for both client A and B | PASS | Has failed in the past
7 | 10 | 7-10 |  |  |  | Partial | Experiment Details Perspective | Alter the name information to include utf8 character in the forenames string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø surname" | Name is utf8 string in Table for both client A and B | PASS | Has failed in the past
7 | 11 | 7-11 |  |  |  | Partial | Experiment Details Perspective | Alter the institute to include the utf8 characters "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Institute is utf8 string in Table for both client A and B | PASS | Has failed in the past
8 | 11 | 8-11 | - | - | - | Difficult | IOC log perspective | Switches correctly when instrument is switched | The log messages switch correctly when the instrument is switched | PASS
8 | 13 | 8-13 | 1521 |  | No | No | IOC log perspective | Generate 150,000 and check gui works | Gui should remain responsive as messages are coming in. Last message should be displayed before new next info message appears. (i.e. the view is refreshed for the last message) | PASS | The gui is filtering out requests to refresh the message view but this means the last refresh may not be caught hence the check on the last message.
8 | 15 | 8-15 |  |  |  |  | Log plotter perspective | Displays a block history (via the block menu) |  | PASS
12 | 5 | 12-5 |  |  |  |  | OPIs | Check the HVCAEN OPI allows you to see and edit the list of channels |  | PASS
13 | 3 | 13-3 |  |  |  | No | Web Links Perspective | Links open the correct web pages |  | PASS | "Launch maintenance website" is linked to instrument name and will 404 on dev instruments
15 | 0 | 15-0 |  |  |  | No | Configs | Open the java visual VM in C:\Program Files (x86)\Java\jdk<version>\bin\jvisualvm.exe and point it at the IBEX GUI. Keep it open through all the system tests to do with configurations. | This is not a test in itself, but will be necessary for test 15-59 later on! | N/A
15 | 50 | 15-50 |  |  |  | No | Configs | All configs can be viewed via their config name PV from a remote system. Example on NDXIRISTEST: 1. Run caget -S -t IN:IRISTEST:CS:BLOCKSERVER:CONFIGS ¦ uzhex 2. Find the PV for the config you want to view 3. Run caget -S -t IN:IRISTEST:CS:BLOCKSERVER:<>pv name:GET_CONFIG_DETAILS ¦ uzhex |  | PASS
15 | 54 | 15-54 |  |  |  |  | Configs within the system | Set a macro via the GUI |  | PASS
15 | 55 | 15-55 |  |  |  | No | Configs within the system | Verify that config changes are pushed to the repo (changes are only passed once per 5 minutes) |  | PASS
15 | 59 | 15-59 |  |  |  | No | Configs | After doing all of the above system tests, check that memory usage is not excessive. This can be done using the java visual VM which was opened in 15-0. Detailed instructions: https://github.com/ISISComputingGroup/ibex_developers_manual/wiki/Debugging-memory-leaks-in-the-IBEX-GUI | While doing all the 15-x tests, memory usage should be fluctuating between 100 and 200MB on average, with no upward trend over a long time period (fluctuations are normal). | N/A
15 | 61 | 15-61 |  |  |  | No | Configs | Create a new config with an IOC which is affected by macros. Set macros in config Save and load the config Check that IOC has macros set in it Edit the current config changing a macro value, adding a value and removing/clearing a value Save Check that the IOC is restarted and that it now obeys the new macro settings | While doing all the 15-x tests, memory usage should be fluctuating between 100 and 200MB on average, with no upward trend over a long time period (fluctuations are normal). | PASS
15 | 62 | 15-62 |  |  |  | No | Configs | Create a new config with an IOC which is affected by macros. Set macros in config Save and load the config Check that IOC has macros set in it Edit a config (not the current config) changing a macro value, adding a value and removing/clearing a value Check macros of running IOC are unaffected |  | PASS
16 | 20 | 16-20 |  |  |  | Maybe | Synoptics | All synoptics can be loaded on a remote instrument (especially synoptics with lots of components) |  | PASS
20 | 1 | 20-1 |  |  |  | Perhaps | Motors | Create blocks looking at motors, and vary the run control limits to see the violations change |  | PASS
20 | 2 | 20-2 |  |  |  | Perhaps | Motors | In a scripting window run the two commands waitfor_move("motor1", "motor2") to check when the motors stop. Also run check_limit_violations("motor1", "motor2") to see soft limit violations within the motor |  | PASS
22 | 1 | 22-1 |  |  |  | Perhaps | Instrument List | Local host name appears at the top of the instrument list when on a host machine |  | PASS
22 | 2 | 22-2 |  |  |  | Yes | Instrument List | When on an instrument machine for an instrument in CS:INSTLIST, the instrument name only appears once and it is at the top of the list |  | PASS
22 | 4 | 22-4 |  |  |  | Yes | Instrument List | Can switch from local host to other instrument |  | PASS
22 | 5 | 22-5 |  |  |  | Yes | Instrument List | Can switch between two listed instruments |  | PASS
22 | 6 | 22-6 |  |  |  | Yes | Instrument List | Can switch to a custom instrument not on the list |  | PASS | Can connect to machines on R3, R80, R55 networks.
23 | 1 | 23-1 |  |  |  | No | Config Version Control | New configurations get added to the local repository if on a branch named after your system |  | PASS
23 | 2 | 23-2 |  |  |  | No | Config Version Control | Config changes get committed to the local repository if on a branch named after your system |  | PASS
23 | 3 | 23-3 |  |  |  | No | Config Version Control | Config changes get pushed to remote repository if on a branch named after your system |  | PASS
23 | 4 | 23-4 |  |  |  | No | Config Version Control | Config changes do not get committed if on a branch starting with ND that is not your system name |  | PASS
23 | 5 | 23-5 |  |  |  | No | Config Version Control | Configs starting with rcptt_ are not added to a repo |  | PASS
24 | 1 | 24-1 |  |  |  | No | Config Version Control | Synoptics starting with rcptt_ are not added to a repo |  | FAIL
25 | 1 | 25-1 |  |  |  | No | Read-only access | Current configuration can be viewed on instruments where you do not have write access |  | PASS
25 | 2 | 25-2 |  |  |  | No | Read-only access | Configurations can not be edited on instruments where you do not have write access |  | PASS
25 | 3 | 25-3 |  |  |  | No | Read-only access | Right-click edit block does not work on read-only instruments |  | PASS
26 | 2 | 26-2 |  |  |  | Perhaps | Help | Switch to a different instrument. Repeat above |  | PASS
27 | 1 | 27-1 |  |  |  | Perhaps | Keyboard shortcuts | Holding ALT and SHIFT causes hotkeys to become underlined in perspective switcher |  | FAIL
27 | 2 | 27-2 |  |  |  | Perhaps | Keyboard shortcuts | Pressing ALT + SHIFT + underlined key switches perspectives |  | FAIL
27 | 3 | 27-3 |  |  |  | Perhaps | Keyboard shortcuts | Confirm that you can access menu items with ALT + underlined key |  | FAIL
27 | 4 | 27-4 |  |  |  | Perhaps | Keyboard shortcuts | Holding SHIFT whilst pressing any key multiple times does not cause changes to perspective switcher text |  | PASS
29 | 1 | 29-1 |  |  |  |  | Script Generator | Clicking the Preview Script button brings up a popup window containing a preview of the generated script. |  | SKIPPED | Note that if the Script Generator perspective is not present, use CTRL+ALT+P to access the preferences menu, go to ISIS perspectives and add the Script Generator. You'll need to restart the GUI
29 | 2 | 29-2 |  |  |  |  | Script Generator | Clicking the Write Script button allows the user to write the script to a python file at a chosen location |  | SKIPPED
29 | 3 | 29-3 |  |  |  |  | Script Generator | Add some values to the table on multiple rows. Click the Clear Table button. | All rows are empty of data. | SKIPPED
29 | 4 | 29-4 |  |  |  |  | Script Generator | Add a Row by setting a non-blank position value. | All the columns, except sample_name, are filled with default values | SKIPPED
29 | 5 | 29-5 |  |  |  |  | Script Generator | Deleting a Row by setting a blank position value clears the rest of the columns. |  | SKIPPED
29 | 6 | 29-6 |  |  |  |  | Script Generator | Setting the Sample Geometry to "Disc" links the Sample Height and Width parameters (independent otherwise) |  | SKIPPED
30 | 1 | 30-1 |  |  | No | Maybe | Preferences | Open the GUI without opening the motors perspective. Change the colour scheme in the Preferences menu. Verify that the table of motors colours background have changed. |  | PASS
30 | 2 | 30-2 |  |  | No | Maybe | Preferences | With the motors perspective open, change the colour scheme in the Preferences menu. Verify that the table of motors background colours have changed. |  | PASS
31 | 1 | 31-1 |  |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission for (or is offline) the synoptic menu items are greyed out |  | PASS
31 | 2 | 31-2 |  |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission open the the Configuration submenu items | All items are greyed out | PASS
31 | 3 | 31-3 |  |  | No | No | Menu Items | Whilst pointing to an instrument that you do not have write permission look at the top item of the Configurations menu | Top item is not edit current config but is view curent config | PASS
31 | 4 | 31-4 |  |  | No | No | Menu items | Check that you can login to "manager mode" with the instrument scientist password. (Ibex menu -> manager mode). Check that the banner item indicates that you have succesfully entered manager mode (you should see "manager mode: active" in red). |  | PASS | Cannot be automated because this test uses a password.
31 | 5 | 31-5 |  |  | No | No | Menu items | Check that you can log out from "manager mode" after performing the above test. |  | PASS
32 | 1 | 32-1 |  |  | No | Yes | JournalViewer | Check the Journalviewer can establish a connection to the database | Status at the bottom shows last refresh time | PASS
32 | 2 | 32-2 |  |  | No | No | JournalViewer | Check the Journalviewer handles failure to establish a connection properly. Change to a nonsense machine (e.g. abcdedg). | Status at the bottom shows highlighted error message in red. | PASS
32 | 3 | 32-3 |  |  | No | No | JournalViewer | Confirm the manual "Refresh" button works. |  | PASS

## Automatable Tests
section no | test number | Test Number | Relates to Ticket# | Relates to Footrpints ID | Is automated | Could be automated | Brief description of task/issue/function | Brief description of test | Expected Outcome | Pass/Fail | Comments
4 | 1 | 4-1 |  |  |  | Yes | Alarms Perspective | Opens when the button is selected | The alarm perspetive opens in the current view field | PASS
6 | 13 | 6-13 |  |  |  | YES | DAE Perspective | Run Summary Tab: Log message table only shows messages with a severity equal or higher than the filter value specified in the drop down menu |  | PASS
6 | 16 | 6-16 |  |  |  | YES | DAE Perspective | Experiment Setup, Data Acquisition: selecting new wiring/detector/spectra table file does not update the current table |  | PASS
6 | 17 | 6-17 |  |  |  | YES | DAE Perspective | Experiment Setup, Data Acquisition: selecting new wiring/detector/spectra table file updates the current table after clicking Apply Changes |  | PASS
6 | 18 | 6-18 |  |  |  | YES | DAE Perspective | Experiment Setup, Periods: selecting a new period file does not update the current file |  | PASS
6 | 19 | 6-19 |  |  |  | YES | DAE Perspective | Experiment Setup, Periods: selecting a new period file updates the current file after clicking Apply Changes |  | PASS
6 | 20 | 6-20 |  |  |  | Hard | DAE Perspective | Check that spectra plots appear. Check that you can change the Y axis type and that this is reflected in the graph's Y axis. |  | PASS | No actual data available at time of testing so just checked that blank plots appear and that the Y axis label updates properly when changing axis type
6 | 21 | 6-21 |  |  |  | Yes | DAE Perspective | When you have no TCB files in your settings then the error message in the TCB file dropdown points to the correct location to place files |  | PASS | Fixed at ticket 2825 for NDX machines
6 | 22 | 6-22 |  |  |  | Yes | DAE Perspective | As above for wiring tables |  | PASS
6 | 23 | 6-23 |  |  |  | Yes | DAE Perspective | As above for detector tables |  | PASS
6 | 24 | 6-24 |  |  |  | Yes | DAE Perspective | As above for spectra tables |  | PASS
6 | 25 | 6-25 |  |  |  | Yes | DAE Perspective | As above for period files |  | PASS
6 | 26 | 6-26 |  |  |  | Yes | DAE Perspective | Create a block called [PVPREFIX]:DAE:TITLE:DISPLAY. Check its value when the "Show DAE title on web dashboard" box is ticked/unticked in the DAE run summary | Unticked: No. Ticked: Yes | PASS | Previously automated but system test became unstable
7 | 2 | 7-2 |  |  |  | Yes | Experiment Details Perspective | Can set a RB number of an actual Experimental Team |  | PASS
7 | 4 | 7-4 |  |  |  | Yes | Experiment Details Perspective | Can search for an RB number by user name |  | PASS
7 | 9 | 7-9 |  |  |  | Partial | Experiment Details Perspective | Alter the name information to include utf8 characters in the name string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Name is utf8 string in both Users (in banner) and Table for both client A and B | PASS | Has failed in the past
7 | 10 | 7-10 |  |  |  | Partial | Experiment Details Perspective | Alter the name information to include utf8 character in the forenames string "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø surname" | Name is utf8 string in Table for both client A and B | PASS | Has failed in the past
7 | 11 | 7-11 |  |  |  | Partial | Experiment Details Perspective | Alter the institute to include the utf8 characters "₣·₤·₥·₦·₧·₨·₩·₪·₫·₭·₮·₯·₹·ø" | Institute is utf8 string in Table for both client A and B | PASS | Has failed in the past
8 | 1 | 8-1 |  |  |  | Yes | IOC log perspective | Opens when the button is selected |  | PASS
8 | 2 | 8-2 |  |  |  | Yes | IOC log perspective | Can show info messages |  | PASS
8 | 3 | 8-3 |  |  |  | Yes | IOC log perspective | Can limit the messages to content value |  | PASS
8 | 4 | 8-4 |  |  |  | Yes | IOC log perspective | Can limit the messages to a date range |  | PASS
8 | 5 | 8-5 |  |  |  | Yes | IOC log perspective | Can limit the messages to a sender |  | PASS
8 | 6 | 8-6 |  |  |  | Yes | IOC log perspective | Can limit the messages to a sender host |  | PASS
8 | 7 | 8-7 |  |  |  | Yes | IOC log perspective | Can limit the messages to a severity |  | PASS
8 | 8 | 8-8 |  |  |  | Yes | IOC log perspective | Can limit the messages to a Type |  | PASS
8 | 9 | 8-9 |  |  |  | Yes | IOC log perspective | Can limit the messages to an Application ID |  | ??
8 | 10 | 8-10 |  |  |  | Yes | IOC log perspective | Can clear the search criteria |  | PASS
8 | 12 | 8-12 |  |  | No | Yes | IOC log perspective | Use the message simulator to create messages of different types. | Messages with higher severity than the filter are shown. | PASS
8 | 14 | 8-14 |  |  | partially | yes | Log plotter perspective | If no blocks selected, displays message explaining how to view block history |  | PASS
13 | 1 | 13-1 |  |  | Yes | Yes | Web Links Perspective | Links are displayed in perspective and work. |  | PASS
15 | 0 | 15-0 |  |  |  | No | Configs | Open the java visual VM in C:\Program Files\Java\jdk1.8.0_73\bin\jvisualvm.exe and point it at the IBEX GUI. Keep it open through all the system tests to do with configurations. | This is not a test in itself, but will be necessary for test 15-59 later on! | N/A
15 | 1 | 15-1 |  |  |  | Yes | Configs | Edit the current config (add an IOC), and save it, changes stored |  | PASS
15 | 2 | 15-2 |  |  |  | Yes | Configs | Edit the current config (add an IOC) and cancel, no changes seen |  | PASS
15 | 3 | 15-3 |  |  |  | Yes | Configs | Edit the current config (add a block), and save it, changes stored |  | PASS
15 | 4 | 15-4 |  |  |  | Yes | Configs | Edit the current config (add a block) and cancel, no changes seen |  | PASS
15 | 5 | 15-5 |  |  |  | Yes | Configs | Edit the current config (add a group), and save it, changes stored |  | PASS
15 | 6 | 15-6 |  |  |  | Yes | Configs | Edit the current config (add a group) and cancel, no changes seen |  | PASS
15 | 7 | 15-7 |  |  |  | Yes | Configs | Edit the current config (select a component), and save it, changes stored |  | PASS
15 | 8 | 15-8 |  |  |  | Yes | Configs | Edit the current config (select a component) and cancel, no changes seen |  | PASS
15 | 9 | 15-9 |  |  |  | Yes | Configs | Edit the current config (set IOC macro), and save it, changes stored. Verify that the changes have been applied at the IOC level |  | PASS
15 | 10 | 15-10 |  |  |  | Yes | Configs | Edit the current config (set IOC macro) and cancel, no changes seen |  | PASS
15 | 11 | 15-11 |  |  |  | Yes | Configs | Create a new config. Click 'Save As'. Enter the name of the current configuration. An error message appears saying the operation is invalid and the 'OK' button remains disabled. |  | PASS
15 | 12 | 15-12 |  |  |  | Yes | Configs | Create a new config. Click save. Enter the name of another configuration. When you click ok, a confirmation box appears asking whether you want to overwrite the existing configuration |  | PASS
15 | 13 | 15-13 |  |  |  | Yes | Configs | Edit a config (not current) by setting some IOC macros. Load the config. Verify the new macro values are displayed in the config and that they are applied to the respective IOCs |  | PASS
15 | 14 | 15-14 |  |  |  | Yes | Configs | Edit the current config (IOC PV values), and save it, changes stored |  | PASS
15 | 15 | 15-15 |  |  |  | Yes | Configs | Edit the current config (IOC PV values) and cancel, no changes seen |  | PASS
15 | 16 | 15-16 |  |  |  | Yes | Configs | Edit the current config (IOC PV sets), and save it, changes stored |  | N/A
15 | 17 | 15-17 |  |  |  | Yes | Configs | Edit the current config (IOC pv sets) and cancel, no changes seen |  | N/A
15 | 18 | 15-18 |  |  |  | Yes | Configs | Edit the current config (summary: description and synoptic), and save it, changes stored |  | PASS
15 | 19 | 15-19 |  |  |  | Yes | Configs | Edit the current config and cancel (summary: description and synoptic), no changes seen |  | PASS
15 | 20 | 15-20 |  |  |  | Yes | Configs | Edit an existing config, and store |  | PASS
15 | 21 | 15-21 |  |  |  | Yes | Configs | Create a new config, and store it |  | PASS
15 | 22 | 15-22 |  |  |  | Yes | Configs | Delete a config |  | PASS
15 | 23 | 15-23 |  |  |  | Yes | Configs | Delete multiple configs simultaneously |  | PASS
15 | 24 | 15-24 |  |  |  | Yes | Configs | Load a config |  | PASS
15 | 25 | 15-25 |  |  |  | Yes | Configs | Create a new config and save as component |  | PASS
15 | 26 | 15-26 |  |  |  | Yes | Configs | Create a new component |  | PASS
15 | 27 | 15-27 |  |  |  | Yes | Configs | Edit a component |  | PASS
15 | 28 | 15-28 |  |  |  | Yes | Configs | Delete a component |  | PASS
15 | 29 | 15-29 |  |  |  | Yes | Configs | Add a block, verifying that the PV search works |  | PASS
15 | 30 | 15-30 |  |  |  | Yes | Configs | Edit a block |  | PASS
15 | 31 | 15-31 |  |  |  | Yes | Configs | Delete a block |  | PASS
15 | 32 | 15-32 |  |  |  | Yes | Configs | A block can be created with run control |  | PASS
15 | 33 | 15-33 |  |  |  | Yes | Configs | New block log settings default to enabled and 30 s rate of periodic scan |  | PASS
15 | 34 | 15-34 |  |  |  | Yes | Configs | A block can be created with logging |  | PASS
15 | 35 | 15-35 |  |  |  | Yes | Configs | Run control can be turned off for a block in the config |  | PASS
15 | 36 | 15-36 |  |  |  | Yes | Configs | Logging can be turned off for a block |  | PASS
15 | 37 | 15-37 |  |  |  | Yes | Configs | Run control can be reinstated for a block via the config editor |  | PASS
15 | 38 | 15-38 |  |  |  | Yes | Configs | Logging can be reinstated for a block via the config editor |  | PASS
15 | 41 | 15-41 |  |  |  | Yes | Configs | Remove blocks from the group |  | PASS
15 | 42 | 15-42 |  |  |  | Yes | Configs | Remove a group |  | PASS
15 | 45 | 15-45 |  |  |  | Yes | Configs | Add some values to the IOC macros |  | PASS
15 | 47 | 15-47 |  |  |  | Yes | Configs | Add a default synoptic to a config |  | PASS
15 | 48 | 15-48 |  |  |  | Yes | Configs | Edit the default synoptic of a config |  | PASS
15 | 49 | 15-49 |  |  |  | Yes | Configs | Remove the default synoptic of a config |  | PASS
15 | 51 | 15-51 |  |  |  | Yes | Configs | Create a block with a pv which has a field (VAL, HLM on a motor) check the values are correct |  | PASS
15 | 52 | 15-52 |  |  |  | Yes | Configs within the system | Set 1 IOCs to Auto Start, 1 IOC Auto restart, 1 IOC to both, 1 IOC to neither in a config. Load that config. Confirm the two IOCs with Auto Start set have started. |  | PASS
15 | 53 | 15-53 |  |  |  | Yes | Configs within the system | Edit a component of the current config, get an idea of length of time for config to reload, pass at <10s |  | PASS
15 | 56 | 15-56 |  |  |  | Yes | Configs within the system | If an IOC is running, but is not in the config, when the config is loaded, the IOC is stopped |  | PASS
15 | 57 | 15-57 |  |  |  | Yes | Configs | Create a new configuration. Click `save as`. Try adding spaces (start, middle and end of name) and special characters. Name should only support alpha-numeric characters and underscores. Error appears otherwise and config cannot be saved |  | PASS
15 | 58 | 15-58 |  |  |  | Yes | Configs | 1. Create a configuration. Add an IOC. Set it to auto-start and put it in recsim mode. Save the config. 2. Edit the config, change the sim level to None. Save the config. | 1. Verify the IOC starts. 2. Verify that the Block Server restarts the IOC | PASS
15 | 63 | 15-63 |  |  |  | Yes | Configs | Create a config with an 2 IOCs in. Load it Remove an ioc and add a different IOC Check that config has the correct IOCs in it. |  | PASS
15 | 64 | 15-64 |  |  |  | Yes | Configs | Add an IOC with custom settings (e.g. recsim) to a component Add the component to a config Load the config and run the IOC Confirm it has the settings set in component |  | PASS
15 | 65 | 15-65 |  |  |  | Yes | Configs | Create a configuration. Set a default synoptic and save Verify the previously selected synoptic is set as this configuration's default synoptic. Verify this works when the default synoptic of the configuration being edited is different from the default synoptic in the currently active configuration |  | PASS
15 | 66 | 15-66 |  |  |  | Yes | Configs | Create a synoptic. Create a new configuration with that synoptic as default. Save. Delete the synoptic | The synoptic will be deleted and no IOC error will be generated | FAIL
15 | 67 | 15-67 |  |  |  | Yes | Configs | Change the description in the current config, save. Verify Gateway, Runcontrol, Archiver and IOCs don't restart. |  | PASS
15 | 68 | 15-68 |  |  |  | Yes | Configs | Change blocks in the current config, save. Verify Gateway, Runcontrol, and Archiver restart. |  | PASS
16 | 9 | 16-9 |  |  |  | Yes | Synoptics | Add a component and select a target (e.g. Analyser). Verify that the appropriate target details come up |  | PASS
16 | 10 | 16-10 |  |  |  | Yes | Synoptics | Using the Analyser*, alter the component target details to be something else, and verify that they change (*or whichever you picked in the previous test) |  | PASS
16 | 11 | 16-11 |  |  |  | Yes | Synoptics | Confirm you can set a custom icon on the Analyser*, which persists when you change the target. Confirm this persists after saving and reopening the dialog. |  | PASS
16 | 12 | 16-12 |  |  |  | Yes | Synoptics | On the Analyser*, confirm the "Clear" button works (i.e. resets to an undefined component) and that subsequently selecting a target sets the correct default icon. |  | PASS
16 | 13 | 16-13 |  |  |  | Yes | Synoptics | Create a component and set DAE as a custom icon. Confirm that clicking on that component in the synoptic opens the DAE perspective |  | FAIL
16 | 18 | 16-18 |  |  |  | Yes | Synoptics | Adding a New PV to a component gives it a default name that is unique (for that component) |  | PASS
16 | 19 | 16-19 |  |  |  | Yes | Synoptics | Cannot add multiple components with the same name to a synoptic |  | PASS | can still preview synoptic
16 | 21 | 16-21 |  |  |  | Yes | Synoptics within the system | Create a synoptic that shows the beam, load it and verify that the beam is there |  | PASS
16 | 22 | 16-22 |  |  |  | Yes | Synoptics within the system | Create a synoptic that doesn't shows the beam, load it and verify that the beam is not there |  | PASS
16 | 23 | 16-23 |  |  |  | Yes | Synoptics within the system | The synoptic is available immediately |  | PASS
16 | 24 | 16-24 |  |  |  | Yes | Synoptics within the system | A synoptic can be edited after saving using "save as" |  | PASS
16 | 25 | 16-25 |  |  |  | Yes | Synoptics within the system | Add a component to a synoptic. Change its type at least twice. Confirm that each time the target details switch to the default for the selected type |  | PASS
16 | 26 | 16-26 |  |  |  | Yes | Synoptics | Open the Synoptic perspective. Verify the synoptic selected in the drop down menu by default is the current configuration's default synoptic |  | PASS
16 | 27 | 16-27 |  |  |  | Yes | Synoptics | With the synoptic perspective open, verify that switching configurations automatically brings up the new configurations default synoptic |  | PASS
16 | 28 | 16-28 |  |  |  | Yes | Synoptics | In the synoptic perspective, verify that pushing the "Load Default" button selects the current configurations default synoptic in the adjacent drop down menu. |  | PASS
17 | 2 | 17-2 |  |  |  | Yes | IOC Start/Stop | Using the console, stop an IOC set to auto-restart in the config, and verify that it restarts |  | PASS
17 | 4 | 17-4 |  |  |  | Yes | IOC Start/Stop | Confirm the "Restart" button in the start/stop IOC dialog works (both for IOC with and without "auto-restart" enabled. |  | PASS
19 | 1 | 19-1 |  |  |  | Yes | OPIs and IOCs | With an IOC started, open OPI, get an idea of length of time before blocks are connected | Pass at <5 seconds | PASS
19 | 2 | 19-2 |  |  |  | Yes | OPIs and IOCs | With an OPI open , Start IOC, get an idea of length of time before pvs are connected | pass at <5s | PASS | Typically in the region 60s for immediate and 5 mins for switch off for 2; and 2:30 for connect ioc after OPI is open
19 | 3 | 19-3 |  |  |  | Yes | OPIs and IOCs | Start IOC, open OPI, Restart IOC, get an idea of length of time, pass at <5 seconds |  | FAIL
19 | 4 | 19-4 |  |  |  | Yes | OPIs and IOCs | Start IOC, open OPI, Stop IOC, Wait 2 minutes, Restart IOC, get an idea of length of time before pvs reconnnect | pass at <60 seconds | PASS
19 | 5 | 19-5 |  |  |  | Yes | OPIs and IOCs | Open OPI, Wait 2 minutes, Start IOC, get an idea of length of time, pass at <5s |  | PASS
21 | 2 | 21-2 |  |  |  | Yes | Blocks | Disconnect a connected block, verify it appears disconnected within 5s |  | PASS
21 | 3 | 21-3 |  |  |  | Yes | Blocks | Reconnect a disconnected block, verify it appears connected within 5s (check various disconnection times up to 5mins) |  | PASS | Typically in the region 10-20s
21 | 6 | 21-6 |  |  |  |  | Blocks | Verify that an orange border appears around blocks in a MINOR-alarm state (.SEVR field) |  | PASS
21 | 7 | 21-7 |  |  |  |  | Blocks | Verify that a red border appears around blocks in an MAJOR-alarm state (.SEVR field) |  | PASS
21 | 8 | 21-8 |  |  |  |  | Blocks | Verify that a purple border appears around blocks in an INVALID-alarm state (.SEVR field) |  | PASS
21 | 26 | 21-26 |  |  |  | Yes | Blocks | Create a hidden block. Right click on any group and confirm that you can switch between showing and hiding the block. |  | PASS
21 | 27 | 21-27 |  |  |  | Yes | Blocks | Create a hidden block. Right click on the block and confirm that you can switch between showing and hiding the block. |  | PASS
22 | 2 | 22-2 |  |  |  | Yes | Instrument List | When on an instrument machine for an instrument in CS:INSTLIST, the instrument name only appears once and it is at the top of the list |  | PASS | duplicated in non automatable?
22 | 3 | 22-3 |  |  |  | Yes | Instrument List | List of supported instruments appears in the instrument list (IBEX > Switch Instrument…) |  | PASS
26 | 1 | 26-1 |  |  |  | Yes | Help | Open the about dialog from the help menu. The server version and client version are displayed correctly |  | PASS | duplicated in non automatable?
27 | 1 | 27-1 |  |  | No | Yes | genie_python | While the DAE is in a state it can begin a run: Load the script "genie_python_dae.py" found in the testing area of the developer manual from the scripting perspective using g.load_script(<script_name>). Run script . Check that no assertions are violated and prompted behaviours are observed |  | PASS
27 | 2 | 27-2 |  |  | No | Yes | genie_python | As above in a genie_python console |  | PASS
27 | 3 | 27-3 |  |  | No | Yes | genie_python | Create a config with SIMPLE IOC and blocks TEST_BLOCK_NUM (SIMPLE:VALUE:P5) and TEST_BLOCK_STR (SIMPLE:HELLO). Run the SIMPLE IOC. Run script "genie_python_blocks.py" from the testing area of the developer manual. Check that no assertions are violated and prompted behaviours are observed |  | PASS
27 | 4 | 27-4 |  |  | No | Yes | genie_python | As above in a genie_python console |  | PASS
27 | 5 | 27-5 |  |  | No | No | genie_python | From a genie_python console (i.e. from the GUI) run `g.plot_spectrum(1)` | A matplotlib window should appear with a sensible plot (probably a flat line for a simulated instrument). No error message should appear in the scripting window | PASS
28 | 1 | 28-1 |  |  | No | Yes | Device screen | Add a device screen and select 'Remove this device when IBEX is closed'. Restart the client | Device screen is removed from device screens list after restart | PASS | Previously automated but system test became unstable
28 | 2 | 28-2 | [5 empty] | Add a device screen and select 'save this device screen'. Restart the client | Device screen is preserved on the device screens list after restart | PASS
29 | 1 | 29-1 |  |  | No | Yes | motors | Open a motor OPI from the motors perspective. Switch instrument | The open OPI should close | PASS
30 | 1 | 30-1 | 3213 |  | No | Yes | Menu items | Verify that the manager mode dialog can be opened first time. From GUI go to IBEX menu -> Manager mode. | The dialog should either ask you for a password if you aren't in manager mode already, or ask you if you want to leave manager mode if you were. | PASS

## Bugs
Bug Number | Fix, Ticket Ignore | Ticket Number (when added to git) | Title | From Test | Description (Description of what is wrong) | Steps to Reproduce
1 | Ignore |  |  | 27-3 | genie_python block tests don't work in scripting window | run genie_python_blocks.py test with correct block. The questions wont appear and the test will hang after 'test setting run-control'. Possibly an issue with assert_from_user_input funtion
2 | Ignore |  |  | 22-6 | Cannot scitch to some custon instrument not on list | try to switch to NDXSCIDEMO, NDXTEST1
3 | Ticket for release |  |  | 15-66 | Cannot delete synoptic. Dialog does not show | try to delete a synotpic
4 | Ticket (no priority) |  |  | 27-(1..3) | Keyboard shortcuts don't work. Probably E4 change | try to use ALT + SHIFT shortcuts
5 | Ignore |  |  | 19-3 | Restarting IOC takes a long time to reconnect PVs in OPI (10+ seconds) | restart IOC when looking at OPI
6 | Ticket (no priority) |  |  | 24-1 | Synoptics starting with rcptt_ are added to a repo | Create synoptic with that prefix and wait 5 mins
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Automated
section no | test number | Test Number | Relates to Ticket# | Relates to Footrpints ID | Brief description of task/issue/function | Brief description of test | Expected Outcome | Comments
1 | 1 | 1-1 |  |  | The server starts in an appropriate way | start_inst runs | no errors
1 | 2 | 1-2 |  |  | The server starts in an appropriate way | ISISDAE_01 runs (open console and type ENTER, verify its log is updated. Check log for no obvious errors)
1 | 5 | 1-5 |  |  | The server starts in an appropriate way | BLOCKSVR runs (as above)
3 | 1 | 3-1 |  |  | The GUI start in an appropriate way | Gui launches
3 | 4 | 3-4 |  |  | Blocks Perspective | Blocks load according to the current config
3 | 7 | 3-7 |  |  | Buttons perspective is working | Can switch between perspectives
6 | 11 | 6-11 |  |  | DAE Perspective | Contents of Experiment Setup sub-tabs are disabled when instrument is running |  |  | PASS
6 | 12 | 6-12 |  |  | DAE Perspective | Contents of Experiment Setup sub-tabs are enabled when instrument is NOT running |  |  | PASS
6 | 20 | 6-20 |  |  | DAE Perspective | Experiment Setup, Periods: content of "Period Settings" group changes appropriately depending on "Period Type" Selection | Software: can only r/w number of software periods; Hardware Internal: Hardware period sequences, delay and period source; Hardware External: like hardware internal but with period sequences and frames parameter disabled |  | PASS
6 | 21 | 6-21 |  |  | DAE Perspective | Experiment Setup, Periods: (only applicable for hardware period types) window shows appropriate controls depending on selected period source | "Specify Parameters" shows table with parameters, "Read from file" shows file selection drop down menu. |  | PASS
7 | 1 | 7-1 |  |  | Experiment Details Perspective | Experiment Details Perspective
7 | 5 | 7-5 |  |  | Experiment Details Perspective | Can alter the Team information
12 | 1 | 12-1 |  |  | Synoptic Perspective | Opens when the button is selected
12 | 2 | 12-2 |  |  | Synoptics | Select a synoptic
12 | 3 | 12-3 |  |  | Synoptics | Browse the synoptic navigation
12 | 4 | 12-4 |  |  | Synoptics | Open an OPI (from a synoptic element)
16 | 17 | 16-17 |  |  | Synoptics | Cannot create a synoptic with a name of greater than 30 characters
21 | 1 | 21-1 |  |  | Blocks | Create a block, verify it appears in the blocks panel
21 | 24 | 21-24 |  |  | Blocks | Create a block. Right click on it in the blocks dashboard and select `Edit block`. Change the block. Click cancel. Verify the changes are not applied
21 | 25 | 21-25 |  |  | Blocks | Create a block. Right click on it in the blocks dashboard and select `Edit block`. Change the block. Click ok. Verify the changes are applied
21 | 28 | 21-28 | 1672 |  | Groups | Create a group containing ONLY hidden blocks. Verify that the group is NOT shown, except when the right-click option "Shown hidden blocks" is selected
16 | 1 | 16-1 |  |  | Synoptics | Create a synoptic
16 | 2 | 16-2 |  |  | Synoptics | Edit a synoptic
16 | 3 | 16-3 |  |  | Synoptics | Delete a synoptic
16 | 4 | 16-4 |  |  | Synoptics | Add a component to a synoptic
3 | 3 | 3-3 |  |  | Dashboard Perspective | Dashboard loads with appropriate data
9 | 1 | 9-1 |  |  | Motors Perspective | Opens when the button is selected
9 | 2 | 9-2 |  |  | Motors Perspective | Can switch between the tabs
9 | 3 | 9-3 |  |  | Motors Perspective | Any running motor records are visible
9 | 4 | 9-4 |  |  | Motors Perspective | Double clicking a motor opens the motor OPI
10 | 1 | 10-1 |  |  | Scripting Perspective | Opens when the button is selected |  |  | PASS
10 | 2 | 10-2 |  |  | Scripting Perspective | check scripting console loads, with EPICS/GeniePython support |  |  | PASS
10 | 3 | 10-3 |  |  | Scripting Perspective | Read a block using cget in the scripting console | Value returned in dictonary |  | PASS
10 | 4 | 10-4 |  |  | Scripting Perspective | Set a block in the scripting console | Value set |  | PASS
10 | 5 | 10-5 |  |  | Scripting Perspective | Read a block using cshow | Value returned as string with information after in brackets |  | PASS
10 | 6 | 10-6 |  |  | Scripting Perspective | Read a diconnected block using cget | Value returned as None |  | PASS
10 | 7 | 10-7 |  |  | Scripting Perspective | Read a disconnected block with cshow | Value returned as "*** diconnected ***" |  | PASS
10 | 8 | 10-8 |  |  | Scripting Perspective | start a run from the scripting console |  |  | PASS
10 | 9 | 10-9 |  |  | Scripting Perspective | end a run from the scripting console |  |  | PASS
10 | 10 | 10-10 |  |  | Scripting Perspective | pause a run from the scripting console (start first) |  |  | PASS
10 | 11 | 10-11 |  |  | Scripting Perspective | resume a run from the scripting console (pause first) |  |  | PASS
5 | 1 | 5-1 |  |  | Beam Status Perspective | Opens when the button is selected
5 | 2 | 5-2 |  |  | Beam Status Perspective | The beam status info is shown
5 | 3 | 5-3 |  |  | Beam Status Perspective | MCR news is shown
5 | 4 | 5-4 |  |  | Beam Status Perspective | the beam current is shown
18 | 1 | 18-1 |  |  | Run Control | View the run control settings
18 | 2 | 18-2 |  |  | Run Control | Edit the run control settings
18 | 3 | 18-3 |  |  | Run Control | Restore the configuration values for run control
16 | 5 | 16-5 |  |  | Synoptics | Delete a component from a synoptic
16 | 6 | 16-6 |  |  | Synoptics | Copy a component on a synoptic
16 | 7 | 16-7 |  |  | Synoptics | Delete multiple components from a synoptic
16 | 8 | 16-8 |  |  | Synoptics | Copy multiple components on a synoptic
7 | 3 | 7-3 |  |  | Experiment Details Perspective | Can set a fake RB number
14 | 1 | 14-1 |  |  | Switch Instruments | Switch instruments by typing a known name
14 | 2 | 14-2 |  |  | Switch Instruments | Switch instruments by typing an unknown name and giving it the correct prefix |  | Should probably remain in the manual tests until there is away to check the client pv prefix (#2419)
28 | 1 | 28-1 |  |  | Device Screens | Confirm that you can add/edit/delete Device Screens
28 | 2 | 28-2 |  |  | Device Screens | Confirm that device screens can not be saved if one or more items is not pointing at a target OPI. | If target is blank: Error message is shown naming the offending device screen & ok button is disabled
28 | 3 | 28-3 |  |  | Device Screens | You can add a local device screen
28 | 4 | 28-4 |  |  | Device Screens | Local device screens disappear when the client is closed and reopened
28 | 5 | 28-5 |  |  | Device Screens | Remote device screens do not disappear when the client is closed and reopened
6 | 1 | 6-1 |  |  | DAE Perspective | Opens when the button is selected |  |  | PASS
6 | 3 | 6-3 |  |  | DAE Perspective | Can start run |  |  | PASS
6 | 4 | 6-4 |  |  | DAE Perspective | Can end run |  |  | PASS
6 | 5 | 6-5 |  |  | DAE Perspective | Can pause run (start first) |  |  | PASS
6 | 6 | 6-6 |  |  | DAE Perspective | Can Resume run (pause first) |  |  | PASS
6 | 7 | 6-7 |  |  | DAE Perspective | Can abort run |  |  | PASS
6 | 8 | 6-8 |  |  | DAE Perspective | Can cancel the abort |  |  | PASS
6 | 9 | 6-9 |  |  | DAE Perspective | Can switch between tabs (and sub-tabs) when the instrument is running |  |  | PASS
6 | 10 | 6-10 |  |  | DAE Perspective | Can switch between tabs (and sub-tabs) when the instrument is not running |  |  | PASS
6 | 14 | 6-14 |  |  | DAE Perspective | Experiment Setup, Time Channels: selecting a new time channel file does not update the current file |  |  | PASS
6 | 15 | 6-15 |  |  | DAE Perspective | Experiment Setup, Time Channels: selecting a new time channel file updates the current file when clicking Apply Changes |  |  | PASS
17 | 1 | 17-1 |  |  | IOC Start/Stop | Start an IOC from the menu
17 | 3 | 17-3 |  |  | IOC Start/Stop | Stop an IOC, and verify that it stops
15 | 39 | 15-39 |  |  | Configs | Add a group
15 | 40 | 15-40 |  |  | Configs | Add blocks to the group
15 | 43 | 15-43 |  |  | Configs | Add components to the config
15 | 44 | 15-44 |  |  | Configs | Remove components from the config
21 | 6 | 21-6 |  |  | Blocks | Take a block under run control and remove run control. Verify that the run control icon disappears
21 | 7 | 21-7 |  |  | Blocks | Block pointing at ai: 0 is displayed as 0.000 (PREC 3) and 0.00000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 8 | 21-8 |  |  | Blocks | Block pointing at ai: 0.1 is displayed as 0.100 (PREC 3) and 0.10000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 9 | 21-9 |  |  | Blocks | Block pointing at ai: 0.01 is displayed as 0.010 (PREC 3) and 0.01000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 10 | 21-10 |  |  | Blocks | Block pointing at ai: 0.001 is displayed as 0.001 (PREC 3) and 0.00100 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 11 | 21-11 |  |  | Blocks | Block pointing at ai: -0.001 is displayed as -0.001 (PREC 3) and -0.00100 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 12 | 21-12 |  |  | Blocks | Block pointing at ai: 0.001234 is displayed as 0.001 (PREC 3) and 0.00123 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 13 | 21-13 |  |  | Blocks | Block pointing at ai: -0.001234 is displayed as -0.001 (PREC 3) and -0.00123 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 14 | 21-14 |  |  | Blocks | Block pointing at ai: 0.0009 is displayed as 9.000E-4 (PREC 3) and 9.00000E-4 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 15 | 21-15 |  |  | Blocks | Block pointing at ai: -0.0009 is displayed as -9.000E-4 (PREC 3) and -9.00000E-4 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 16 | 21-16 |  |  | Blocks | Block pointing at ai: 15 is displayed as 15.000 (PREC 3) and 15.00000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 17 | 21-17 |  |  | Blocks | Block pointing at ai: 999999 is displayed as 999999.000 (PREC 3) and 999999.00000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 18 | 21-18 |  |  | Blocks | Block pointing at ai: -999999 is displayed as -999999.000 (PREC 3) and -999999.00000 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 19 | 21-19 |  |  | Blocks | Block pointing at ai: 1000000 is displayed as 1.000E6 (PREC 3) and 1.00000E6 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 20 | 21-20 |  |  | Blocks | Block pointing at ai: -1000000 is displayed as -1.000E6 (PREC 3) and -1.00000E6 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 21 | 21-21 |  |  | Blocks | Block pointing at ai: 1234567 is displayed as 1.235E6 (PREC 3) and 1.23457E7 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 22 | 21-22 |  |  | Blocks | Block pointing at ai: -1234567 is displayed as -1.235E6 (PREC 3) and -1.23457E7 (PREC 5) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG
21 | 23 | 21-23 |  |  | Blocks | Block pointing at longin: never displayed as scientific notation (try 0, 15, 999999, 1000000, 1234567 and their negatives) |  | Can use the following PVs from SIMPLE IOC: VALUE:P3, VALUE:P5, LONG